## Tool Summary
Tool | Category | License | Vendor | Notes | Pricing Notes | Cost Unit | Cost Unit Notes | Phase I Cost Duration | Phase I Cost
Zoo CAD + API Calls | CAD / Analysis / Design | Open-source or commercial | Zoo | Parametric CAD primitives. Easy to integrate. | Baseline pro rate, monthly: https://zoo.dev/design-studio-pricing Inclusive of expected API usage | 2092 | One time | 1 | 2092
Fusion 360 | CAD / Analysis / Design | Commercial | Autodesk | Fallback if NX integration is too heavy. MCP already exists. |  | 680 | Per user per year | 2 | 1360
Python sizing tools for disciplines, Open source infractructure (PyNastran, OpenMDAO, etc.) | CAD / Analysis / Design | Custom / Open Source | Custom / Open Source | Pynastran: extract/modify results OpenMDAO: system engineering optimizations |  | 0 |  | 1 | 0
Traditional Manufacturing DFM Rule Engine | Manufacturing | Custom | Custom | Custom built, simple for Phase I, extensible to more advanced tools later |  | 0 |  | 1 | 0
Additive DFM Engine | Manufacturing | Custom | Custom | Rely on simplistic rule engine for Phase I, determine value of commercial vs. native build option for Phase II |  | 0 |  | 1 | 0
Cost and Leadtime Engine | Manufacturing | Custom | Custom | Custom engine taking in data from other disciplines to best effort cost and leadtime estimate |  | 0 |  | 1 | 0
Standard Hardware Engine | Manufacturing | Custom | Custom | Custom CSV / API, Returns Standard Hardware Recommendations (NAS, etc.) |  | 0 |  | 1 | 0
Database: Mechanisms COTS | CAD / Analysis / Design | Custom | Custom | Custom CSV / API, Returns Sep Mechanism Data |  | 0 |  | 1 | 0
Database: M&P (MMPDS-lite, outgassing, corrosion, SCC, NCAMP/CMH-17) | M&P | Custom | Custom | Custom CSV / API, Returns Material Data |  | 0 |  | 1 | 0
Database: vendor and factory capability | Manufacturing | Custom | Custom | Custom CSV / API, for setting restrictions on what's realistically manufacturable and cost/leadtime estimates |  | 0 |  | 1 | 0
McMaster / Protolabs / Xometry APIs | Manufacturing | Free-Tier | Protolabs/Xometry | Optional / Free Tier, Quote + manufacturability API (CSV or JSON ingestible) |  | 0 |  | 1 | 0
IHS, AIAA, SAE, etc. Access | Knowledge | Commercial | TBD | Reference only, for knowledge database | Include in misc. domain libs/etc. Focus on open source for phase I. | 0 |  | 0 | 0
Flow | Infrastructure | Commercial | Flow | Flow Engineering integration | See in-kind email. | 0 |  | 0 | 0
LangGraph | Infrastructure | Open-source | Langchain | For agentic workflow orchestration |  | 0 |  | 1 | 0
LangSmith | Infrastructure | Commercial | Langchain | For LLM prompt management | Use pro plan to start, extend to 2 users. They also offer extended startup plan costs. https://www.langchain.com/pricing-langsmith SBIR/startup pricing avaialble, not included | 39 | Per user per month | 6 | 292.5
AWS Infrastructure+LLM, Slack, GitHub, Cursor, Office Utilities | Infrastructure | Commercial | Multiple | Bucket for misc tools / prototyping |  | 3000 | One-time | 1 | 3000

## Task estimation
Size | Size2 | Effort rule-of-thumb (one focused engineer) | Min Hr | Max Hr | Typical span in a two-week sprint
S | Small | 0.5 – 1 engineering day (4 – 8 h) | 4 | 8 | Slips comfortably into the slack between bigger tasks; treat as half-day fillers.
M | Medium | 2 – 3 engineering days (16 – 24 h) | 16 | 24 | A solid “block” item that usually fits in one work-week alongside a couple of Smalls.
L | Large | 4 – 5 engineering days (32 – 40 h) | 32 | 40 | Roughly a full week for the person who owns it. If it spills past 5 days, split it.
| 6 focused hrs of work per day | [8 empty] | 0.25 | 0.75 | 1
| Sprint capacity check. | [5 empty] | FTEs |  |  | 0.25 FTE | 0.75 FTE | 1 FTE
|  | In a 2-week sprint (10 working days) with three people: |  |  |  |  | Hrs/wk | 40 |  | 10 | 30 | 40 | 80
|  | Raw capacity ≈ 30 engineer-days. |  |  |  |  | Wks/Sprint | 2 |  | 2 | 2 | 2 | 2 | 0.88542
|  | Subtract ~20 % for unforeseen churn, NASA comms, sprint ceremonies → ~24 bookable days. |  |  |  |  | Hrs/Sprint | 80 |  | 20 | 60 | 80 | 160 | 1920
|  | Using the table above, a healthy sprint mix is something like 3 × L + 3 × M + 6 × S ≈ 22–24 effort-days. |  |  |  |  | FTEs | 2
|  | Max est. hrs/sprint available | 128 |  |  |  | Hrs/Sprint for Team | 160
|  | Max es. Hrs/sprint for 0.75 FTE | 48 |  |  |  | Efficiency | 80%
[7 empty] | Effective max hours | 128 |  | 16 | 48 | 64
Confidence | Confidence2 | Description | Factor |  |  |  | Over entire pop |  |  | 192 | 576 | 768 | 1536
H | High | Easy, routine tasks | 1
M | Medium | Thing I know the team has some experience in | 1.6
L | Low | Testing, demos, deployment | 2
Rate justification | Data Value | Proposal | Sources
Fringe | 29.73% | 30% | BLS Fringe Rate Data What Is the Average Cost of Benefits Per Employee? The Complete Guide ¦ Benepass
Overhead | 15%-25% | 20% | Overhead Rates for Small Businesses ¦ Complete Controller
G&A | 10%-20% | 10% | Acocunting software (Quickbooks), CPA fees. Applied to PI only. A significant amount will be in-kind from contracted Fractional-CFO bench.
Profit | 7% | 0% | Startup, Phase I is to get project off the ground and expand in Phase II+. SBIR Profit Guidance
Role | ID | SOC Code | Annual Wage | Base Hourly Rate | Assumed Fringe % | Assumed Overhead % | Assumed G&A % | Assumed Profit % | Fully Burdened Rate | Source
Principal Investigator / Mechanical Engineer (National) | PI | 17-2141 | 99510 | 47.84 | 30% | 20% | 10% | 0% | 82.0934 | BLS national median 2024
Senior Software Engineer (National) | SWE | 15-1252 | 133080 | 63.98 | 30% | 20% | 10% | 0% | 109.7897 | BLS national median 2024
UX/UI Designer (National) | UI | 15-1255 | 98540 | 47.38 | 30% | 20% | 10% | 0% | 81.3041 | BLS national median 2024
Variable | Units | Value
Assumed efficiency | % | 80%
Materials Budget

## Phase I Personnel Tasks
B - T - D | Sprint | Epic | Objectives | Objectives Completed | Discrete task | Deliverable | Size | PI % | SW % | UI % | Confidence | Confidence Adjustment | Hrs, Min | Hrs, Max | Hrs, Avg | Hrs, Unadjusted, Avg | PI, Hrs, Min | PI, Hrs, Max | PI, Hrs, Avg | SW, Hrs, Min | SW, Hrs, Max | SW, Hrs, Avg | UI, Hrs, Min | UI, Hrs, Max | UI, Hrs, Avg | % Sum Check
Build | 1 | MCP core + schema | 1 3 |  | JSON schema & auto-hash | Repo hashed | L | 50% | 50% | 0% | H | 1 | 32 | 40 | 36 | 36 | 16 | 20 | 18 | 16 | 20 | 18 | 0 | 0 | 0 | 100%
Build | 1 | Agent skeleton | 2 |  | LangGraph bus + Sys-Eng stub | Running bus | M | 75% | 25% | 0% | L | 2 | 32 | 48 | 40 | 20 | 24 | 36 | 30 | 8 | 12 | 10 | 0 | 0 | 0 | 100%
Build | 1 | Secondary stubs | 2 |  | Struct/Mech/M&P/Mfg/Therm echoes | 5 stub agents | M | 50% | 50% | 0% | L | 2 | 32 | 48 | 40 | 20 | 16 | 24 | 20 | 16 | 24 | 20 | 0 | 0 | 0 | 100%
Test | 1 | CI schema-lint | 1 |  | momentum-lint passes | Green CI | S | 20% | 80% | 0% | L | 2 | 8 | 16 | 12 | 6 | 1.6 | 3.2 | 2.4 | 6.4 | 12.8 | 9.6 | 0 | 0 | 0 | 100%
Build | 1 | UI shell skeleton | 4 |  | Dashboard layout scaffold | React nav | S | 30% | 0% | 70% | M | 1.6 | 6.4 | 12.8 | 9.6 | 6 | 1.92 | 3.84 | 2.88 | 0 | 0 | 0 | 4.48 | 8.96 | 6.72 | 100%
Build | 1 | Interface lookup tables | 6 |  | Bolt-pattern & keep-out CSVs | CSVs committed | S | 75% | 25% | 0% | M | 1.6 | 6.4 | 12.8 | 9.6 | 6 | 4.8 | 9.6 | 7.2 | 1.6 | 3.2 | 2.4 | 0 | 0 | 0 | 100%
Buffer | 1 | Buffer Placeholder, Sprint 1 | – |  | — | — | S | 34% | 33% | 33% | H | 1 | 4 | 8 | 6 | 6 | 1.36 | 2.72 | 2.04 | 1.32 | 2.64 | 1.98 | 1.32 | 2.64 | 1.98 | 100%
Build | 2 | Zoo-CAD adapter | 3 |  | JSON↔Zoo I/O | Import script | M | 75% | 25% | 0% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 19.2 | 28.8 | 24 | 6.4 | 9.6 | 8 | 0 | 0 | 0 | 100%
Build | 2 | First-order sizing | 2 |  | Mass & beam scripts | Python lib | M | 75% | 25% | 0% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 19.2 | 28.8 | 24 | 6.4 | 9.6 | 8 | 0 | 0 | 0 | 100%
Build | 2 | Materials DB stub | 5 |  | MMPDS-lite SQLite | DB file | S | 75% | 25% | 0% | M | 1.6 | 6.4 | 12.8 | 9.6 | 6 | 4.8 | 9.6 | 7.2 | 1.6 | 3.2 | 2.4 | 0 | 0 | 0 | 100%
Build | 2 | Structures agent (Basic) | 2 |  | Adapter calc + Zoo model | Margin JSON | M | 50% | 50% | 0% | L | 2 | 32 | 48 | 40 | 20 | 16 | 24 | 20 | 16 | 24 | 20 | 0 | 0 | 0 | 100%
Test | 2 | Basic mission loop | 2 | 1 | Narrative→Zoo→VC hash | VC entry | M | 25% | 75% | 0% | L | 2 | 32 | 48 | 40 | 20 | 8 | 12 | 10 | 24 | 36 | 30 | 0 | 0 | 0 | 100%
Buffer | 2 | Buffer Placeholder, Sprint 2 | – |  | — | — | S | 34% | 33% | 33% | H | 1 | 4 | 8 | 6 | 6 | 1.36 | 2.72 | 2.04 | 1.32 | 2.64 | 1.98 | 1.32 | 2.64 | 1.98 | 100%
Build | 3 | Verification-Chain viewer | 5 |  | Hash viewer page | Web page | M | 50% | 50% | 0% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 12.8 | 19.2 | 16 | 12.8 | 19.2 | 16 | 0 | 0 | 0 | 100%
Build | 3 | Primitives build | 8 |  | Parametric design and analysis tools (CAD, FEA, classical) | Callable tool set | M | 90% | 10% |  | L | 2 | 32 | 48 | 40 | 20 | 28.8 | 43.2 | 36 | 3.2 | 4.8 | 4 | 0 | 0 | 0 | 100%
Build | 3 | Mechanisms & M&P (Basic) | 2 |  | COTS lookup + allowables | Trade sheet + mat JSON | M | 25% | 75% | 0% | L | 2 | 32 | 48 | 40 | 20 | 8 | 12 | 10 | 24 | 36 | 30 | 0 | 0 | 0 | 100%
Build | 3 | UI results panel | 4 |  | Sizing/mass table view | React card | M | 30% | 0% | 70% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 7.68 | 11.52 | 9.6 | 0 | 0 | 0 | 17.92 | 26.88 | 22.4 | 100%
Ship | 3 | Interim loop demo | 2 | 2 | Short GIF | GIF clip | S | 75% | 15% | 10% | M | 1.6 | 6.4 | 12.8 | 9.6 | 6 | 4.8 | 9.6 | 7.2 | 0.96 | 1.92 | 1.44 | 0.64 | 1.28 | 0.96 | 100%
Buffer | 3 | Buffer Placeholder, Sprint 3 | – |  | — | — | M | 34% | 33% | 33% | H | 1 | 16 | 24 | 20 | 20 | 5.44 | 8.16 | 6.8 | 5.28 | 7.92 | 6.6 | 5.28 | 7.92 | 6.6 | 100%
Build | 4 | Billet DFM v1 | 6 |  | Stock-rule YAML | Rule file | M | 75% | 25% | 0% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 19.2 | 28.8 | 24 | 6.4 | 9.6 | 8 | 0 | 0 | 0 | 100%
Build | 4 | Manufacturing agent stub | 6 |  | Mfg echo outputs | JSON stub | M | 50% | 50% | 0% | L | 2 | 32 | 48 | 40 | 20 | 16 | 24 | 20 | 16 | 24 | 20 | 0 | 0 | 0 | 100%
Build | 4 | Simcenter wrapper | 3 |  | Modal & lin-static CLI | — | L | 50% | 50% | 0% | L | 2 | 64 | 80 | 72 | 36 | 32 | 40 | 36 | 32 | 40 | 36 | 0 | 0 | 0 | 100%
Buffer | 4 | Buffer Placeholder, Sprint 4 | – |  | — | — | M | 34% | 33% | 33% | H | 1 | 16 | 24 | 20 | 20 | 5.44 | 8.16 | 6.8 | 5.28 | 7.92 | 6.6 | 5.28 | 7.92 | 6.6 | 100%
Build | 5 | PyNastran adapter | 3 |  | Static-solve CLI | Wrapper | M | 50% | 50% | 0% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 12.8 | 19.2 | 16 | 12.8 | 19.2 | 16 | 0 | 0 | 0 | 100%
Build | 5 | Structures agent (CoDR) | 3 |  | Static margins | Margin CSV | M | 50% | 50% | 0% | L | 2 | 32 | 48 | 40 | 20 | 16 | 24 | 20 | 16 | 24 | 20 | 0 | 0 | 0 | 100%
Build | 5 | Mechanisms & M&P (CoDR) | 2 |  | Trade matrix + alloy | CSV + JSON | M | 50% | 50% | 0% | L | 2 | 32 | 48 | 40 | 20 | 16 | 24 | 20 | 16 | 24 | 20 | 0 | 0 | 0 | 100%
Build | 5 | Structures agent (PDR) | 3 |  | Modal margins | Modal CSV | M | 50% | 50% | 0% | L | 2 | 32 | 48 | 40 | 20 | 16 | 24 | 20 | 16 | 24 | 20 | 0 | 0 | 0 | 100%
Buffer | 5 | Buffer Placeholder, Sprint 5 | – |  | — | — | M | 34% | 33% | 33% | H | 1 | 16 | 24 | 20 | 20 | 5.44 | 8.16 | 6.8 | 5.28 | 7.92 | 6.6 | 5.28 | 7.92 | 6.6 | 100%
Ship | 6 | CoDR deck | 3 |  | Static deck PDF | PDF | S | 75% | 15% | 10% | M | 1.6 | 6.4 | 12.8 | 9.6 | 6 | 4.8 | 9.6 | 7.2 | 0.96 | 1.92 | 1.44 | 0.64 | 1.28 | 0.96 | 100%
Build | 6 | M&P agent (PDR) | 2 |  | Fatigue & temper data | Updated JSON | M | 50% | 50% | 0% | L | 2 | 32 | 48 | 40 | 20 | 16 | 24 | 20 | 16 | 24 | 20 | 0 | 0 | 0 | 100%
Build | 6 | Manufacturing cost engine | 6 |  | Billet cost JSON | Cost file | M | 50% | 50% | 0% | L | 2 | 32 | 48 | 40 | 20 | 16 | 24 | 20 | 16 | 24 | 20 | 0 | 0 | 0 | 100%
Build | 6 | Knowledge dashboards | 4 | 4 | Zoo/VC/DFM views | React pages | M | 10% | 0% | 90% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 2.56 | 3.84 | 3.2 | 0 | 0 | 0 | 23.04 | 34.56 | 28.8 | 100%
Buffer | 6 | Buffer Placeholder, Sprint 6 | – |  | — | — | M | 34% | 33% | 33% | H | 1 | 16 | 24 | 20 | 20 | 5.44 | 8.16 | 6.8 | 5.28 | 7.92 | 6.6 | 5.28 | 7.92 | 6.6 | 100%
Build | 7 | NX-CAD wrapper | 3 |  | JSON↔NX I/O | Rerun workflow | L | 50% | 50% | 0% | L | 2 | 64 | 80 | 72 | 36 | 32 | 40 | 36 | 32 | 40 | 36 | 0 | 0 | 0 | 100%
Test | 7 | Billet DFM regression | 6 |  | Rule loop pass | Pass log | L | 50% | 50% | 0% | L | 2 | 64 | 80 | 72 | 36 | 32 | 40 | 36 | 32 | 40 | 36 | 0 | 0 | 0 | 100%
Ship | 7 | DFM demo clip | 6 | 6 | Fail/fix MP4 | MP4 | S | 70% | 20% | 10% | M | 1.6 | 6.4 | 12.8 | 9.6 | 6 | 4.48 | 8.96 | 6.72 | 1.28 | 2.56 | 1.92 | 0.64 | 1.28 | 0.96 | 100%
Buffer | 7 | Buffer Placeholder, Sprint 7 | – |  | — | — | M | 34% | 33% | 33% | H | 1 | 16 | 24 | 20 | 20 | 5.44 | 8.16 | 6.8 | 5.28 | 7.92 | 6.6 | 5.28 | 7.92 | 6.6 | 100%
Test | 8 | Verification-Chain audit | 5 | 5 | Hash diff email | CI email | S | 45% | 45% | 10% | L | 2 | 8 | 16 | 12 | 6 | 3.6 | 7.2 | 5.4 | 3.6 | 7.2 | 5.4 | 0.8 | 1.6 | 1.2 | 100%
Build | 8 | PDR trade engine | 3 |  | Modal updater script | Python script | L | 45% | 45% | 10% | L | 2 | 64 | 80 | 72 | 36 | 28.8 | 36 | 32.4 | 28.8 | 36 | 32.4 | 6.4 | 8 | 7.2 | 100%
Test | 8 | PDR acceptance | 5 |  | Multi-disc pass | Review log | M | 45% | 45% | 10% | L | 2 | 32 | 48 | 40 | 20 | 14.4 | 21.6 | 18 | 14.4 | 21.6 | 18 | 3.2 | 4.8 | 4 | 100%
Ship | 8 | PDR deck demo | 5 | 3 | PDR deck PDF | PDF | S | 70% | 20% | 10% | M | 1.6 | 6.4 | 12.8 | 9.6 | 6 | 4.48 | 8.96 | 6.72 | 1.28 | 2.56 | 1.92 | 0.64 | 1.28 | 0.96 | 100%
Buffer | 8 | Buffer Placeholder, Sprint 8 | – |  | — | — | M | 34% | 33% | 33% | H | 1 | 16 | 24 | 20 | 20 | 5.44 | 8.16 | 6.8 | 5.28 | 7.92 | 6.6 | 5.28 | 7.92 | 6.6 | 100%
Test | 9 | UX acceptance | 7 |  | Pixel diff < 3 % | Cypress log | M | 10% | 0% | 90% | L | 2 | 32 | 48 | 40 | 20 | 3.2 | 4.8 | 4 | 0 | 0 | 0 | 28.8 | 43.2 | 36 | 100%
Build | 9 | 5x benchmark | 8 | 8 | Mission replay scripts | Timing log | M | 45% | 45% | 10% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 11.52 | 17.28 | 14.4 | 11.52 | 17.28 | 14.4 | 2.56 | 3.84 | 3.2 | 100%
Ship | 9 | OpenAPI bundle + demo | 7 | 7 | Swagger + Postman | JSON | S | 50% | 50% | 0% | M | 1.6 | 6.4 | 12.8 | 9.6 | 6 | 3.2 | 6.4 | 4.8 | 3.2 | 6.4 | 4.8 | 0 | 0 | 0 | 100%
Buffer | 9 | Buffer Placeholder, Sprint 9 | – |  | — | — | M | 34% | 33% | 33% | H | 1 | 16 | 24 | 20 | 20 | 5.44 | 8.16 | 6.8 | 5.28 | 7.92 | 6.6 | 5.28 | 7.92 | 6.6 | 100%
Build | 10 | Evidence builder | 9 |  | Log collector | Bundle | M | 75% | 15% | 10% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 19.2 | 28.8 | 24 | 3.84 | 5.76 | 4.8 | 2.56 | 3.84 | 3.2 | 100%
Test | 10 | Final VC audit | 5, 9 |  | Hash reproduce | Audit rpt | S | 75% | 15% | 10% | L | 2 | 8 | 16 | 12 | 6 | 6 | 12 | 9 | 1.2 | 2.4 | 1.8 | 0.8 | 1.6 | 1.2 | 100%
Buffer | 10 | Buffer Placeholder, Sprint 10 | – |  | — | — | M | 34% | 33% | 33% | H | 1 | 16 | 24 | 20 | 20 | 5.44 | 8.16 | 6.8 | 5.28 | 7.92 | 6.6 | 5.28 | 7.92 | 6.6 | 100%
Ship | 11 | Evidence dossier | 9 |  | Video + logs | PDF + MP4 | M | 75% | 15% | 10% | M | 1.6 | 25.6 | 38.4 | 32 | 20 | 19.2 | 28.8 | 24 | 3.84 | 5.76 | 4.8 | 2.56 | 3.84 | 3.2 | 100%
Buffer | 11 | Buffer Placeholder, Sprint 11 | – |  | — | — | L | 34% | 33% | 33% | H | 1 | 32 | 40 | 36 | 36 | 10.88 | 13.6 | 12.24 | 10.56 | 13.2 | 11.88 | 10.56 | 13.2 | 11.88 | 100%
Ship | 12 | TRL-4 freeze | 9 | 9 | Tag repo + archive | Git tag | S | 34% | 33% | 33% | H | 1 | 4 | 8 | 6 | 6 | 1.36 | 2.72 | 2.04 | 1.32 | 2.64 | 1.98 | 1.32 | 2.64 | 1.98 | 100%
Buffer | 12 | Buffer Placeholder, Sprint 12 | – |  | — | — | L | 34% | 33% | 33% | H | 1 | 32 | 40 | 36 | 36 | 10.88 | 13.6 | 12.24 | 10.56 | 13.2 | 11.88 | 10.56 | 13.2 | 11.88 | 100%
[15 empty] | 1566.8 | 976
[14 empty] | Effective uncertainty | 1.6053
Total buffer

## Phase I Personnel Summary
Sum of Hrs, Avg | B - T - D
Sprint | Build | Ship | Test | Buffer | Grand Total
1 | 135.2 |  | 12 | 6 | 153.2
2 | 113.6 |  | 40 | 6 | 159.6
3 | 144 | 9.6 |  | 20 | 173.6
4 | 144 |  |  | 20 | 164
5 | 152 |  |  | 20 | 172
6 | 112 | 9.6 |  | 20 | 141.6
7 | 72 | 9.6 | 72 | 20 | 173.6
8 | 72 | 9.6 | 52 | 20 | 153.6
9 | 32 | 9.6 | 40 | 20 | 101.6
10 | 32 |  | 12 | 20 | 64
11 |  | 32 |  | 36 | 68
12 |  | 6 |  | 36 | 42
Grand Total | 1008.8 | 86 | 228 | 244 | 1566.8
0.15573
https://chatgpt.com/share/687c7a48-9d60-800a-b8af-ea84ce9e74d9
|  | Average load, without buffer days | 20.3333
| Values | B - T - D
| Sum of UI, Hrs, Avg |  |  |  | Sum of SW, Hrs, Avg |  |  |  | Sum of PI, Hrs, Avg |  |  |  | Total Sum of UI, Hrs, Avg | Total Sum of SW, Hrs, Avg | Total Sum of PI, Hrs, Avg
Sprint | Build | Ship | Test | Buffer | Build | Ship | Test | Buffer | Build | Ship | Test | Buffer
1 | 6.72 |  | 0 | 1.98 | 50.4 |  | 9.6 | 1.98 | 78.08 |  | 2.4 | 2.04 | 8.7 | 61.98 | 82.52
2 | 0 |  | 0 | 1.98 | 38.4 |  | 30 | 1.98 | 75.2 |  | 10 | 2.04 | 1.98 | 70.38 | 87.24
3 | 22.4 | 0.96 |  | 6.6 | 50 | 1.44 |  | 6.6 | 71.6 | 7.2 |  | 6.8 | 29.96 | 58.04 | 85.6
4 | 0 |  |  | 6.6 | 64 |  |  | 6.6 | 80 |  |  | 6.8 | 6.6 | 70.6 | 86.8
5 | 0 |  |  | 6.6 | 76 |  |  | 6.6 | 76 |  |  | 6.8 | 6.6 | 82.6 | 82.8
6 | 28.8 | 0.96 |  | 6.6 | 40 | 1.44 |  | 6.6 | 43.2 | 7.2 |  | 6.8 | 36.36 | 48.04 | 57.2
7 | 0 | 0.96 | 0 | 6.6 | 36 | 1.92 | 36 | 6.6 | 36 | 6.72 | 36 | 6.8 | 7.56 | 80.52 | 85.52
8 | 7.2 | 0.96 | 5.2 | 6.6 | 32.4 | 1.92 | 23.4 | 6.6 | 32.4 | 6.72 | 23.4 | 6.8 | 19.96 | 64.32 | 69.32
9 | 3.2 | 0 | 36 | 6.6 | 14.4 | 4.8 | 0 | 6.6 | 14.4 | 4.8 | 4 | 6.8 | 45.8 | 25.8 | 30
10 | 3.2 |  | 1.2 | 6.6 | 4.8 |  | 1.8 | 6.6 | 24 |  | 9 | 6.8 | 11 | 13.2 | 39.8
11 |  | 3.2 |  | 11.88 |  | 4.8 |  | 11.88 |  | 24 |  | 12.24 | 15.08 | 16.68 | 36.24
12 |  | 1.98 |  | 11.88 |  | 1.98 |  | 11.88 |  | 2.04 |  | 12.24 | 13.86 | 13.86 | 14.28
Grand Total | 71.52 | 9.02 | 42.4 | 80.52 | 406.4 | 18.3 | 100.8 | 80.52 | 530.88 | 58.68 | 84.8 | 82.96 | 203.46 | 606.02 | 757.32
Factor up for cost budget by efficiency assumed
| Efficiency | 0.85
Sprint | Required UI | Required SW | Required PI | Total Team
1 | 10.2353 | 72.9176 | 97.0824 | 180.2353
2 | 2.3294 | 82.8 | 102.6353 | 187.7647
3 | 35.2471 | 68.2824 | 100.7059 | 204.2353
4 | 7.7647 | 83.0588 | 102.1176 | 192.9412
5 | 7.7647 | 97.1765 | 97.4118 | 202.3529
6 | 42.7765 | 56.5176 | 67.2941 | 166.5882
7 | 8.8941 | 94.7294 | 100.6118 | 204.2353
8 | 23.4824 | 75.6706 | 81.5529 | 180.7059
9 | 53.8824 | 30.3529 | 35.2941 | 119.5294
10 | 12.9412 | 15.5294 | 46.8235 | 75.2941
11 | 17.7412 | 19.6235 | 42.6353 | 80
12 | 16.3059 | 16.3059 | 16.8 | 49.4118
Totals | 239.3647 | 712.9647 | 890.9647 | 1843.2941
Sprint | Count of Objectives Completed
1
2 | 1
3 | 1
4
5
6 | 1
7 | 1
8 | 2
9 | 2
10
11
12 | 1
Grand Total | 9
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.